## Slide 1: PROJECT MANAGEMENT
Subtitle

## Slide 2: The Four P’s
People — the most important element of a successful project
Product — the software to be built
Process — the set of framework activities and software engineering tasks to get the job done
Project — all work required to make the product a reality

## Slide 3: Stakeholders
Senior managers who define the business issues that often have significant influence on the project.
Project (technical) managers who must plan, motivate, organize, and control the practitioners who do software work.
Practitioners who deliver the technical skills that are necessary to engineer a product or application.
Customers who specify the requirements for the software to be engineered and other stakeholders who have a peripheral interest in the outcome.
End-users who interact with the software once it is released for production use.

## Slide 4
4
Software Teams
How to lead?
How to organize?
How to motivate?
How to collaborate?
How to create good ideas?
How to lead?
How to collaborate?
How to motivate?
How to create good ideas?
How to organize?

## Slide 5: THE SOFTWARE DEVELOPMENT PLAN (SDP)
the SDP documents exactly how the project will be managed
  it defines the project
first need to define the scope of the development
  define the problem  agree on what constitutes success
  analyze the requirements  so you can make sizing estimates
  prepare a top-level package diagram  overall view of the system
  estimate the time and effort needed to deliver the product
input needed from:
  development manager  project organization, WBS, budget
  experienced system architect  top-level package diagram, project sizing
  expert user or domain expert  requirements understanding

## Slide 6
DESIGNING THE SDP
deliverables
development environment
size and effort estimates
risk planning
lifecycle model
work breakdown structure (WBS)
schedules
staffing and organization
product teams
time-phased budget
metrics plan

## Slide 7
DELIVERABLES
Customer products  given to the customer
Process artifacts  outcomes of the development process
Internal deliverables  of value to organization beyond this project
Services  additional deliverables for the customer

## Slide 8
DEVELOPMENT ENVIRONMENT
need to choose hardware and software development tools appropriate for the project
development tools ≠ development process
tools are effective only if they make well-understood processes more efficient
in choosing a development support tool evaluate:
  support of the lifecycle: UML; management oversight and control; architectural control; collaboration support; developer efficiency; library integration; documentation support
  risk of adoption to both cost and schedule: external cost; internal cost; time loss; product instability; investment protection

## Slide 9
SIZE AND EFFORT ESTIMATES
Estimating: trying to quantify something before it occurs
we usually need to estimate:
  size – effort – duration
  productivity – development cost
based on:
  experience – historical data – courage!
which is facilitated if we:
  establish project scope in advance
  use software metrics from past projects
  divide and conquer
estimating carries inherent risk

## Slide 10
SOFTWARE METRICS FOR ESTIMATING
We can collect many types metrics about many aspects of software.
Question: What metrics are useful for estimating and how can they be used for estimating?
Technical metrics
Quality metrics
Productivity metrics
Size-oriented metrics
Function-oriented metrics
Human-oriented metrics
Productivity metrics
Size-oriented metrics
Function-oriented metrics

## Slide 11
SOFTWARE METRICS FOR ESTIMATING
productivity metrics – focus on the output of the software engineering process
quality metrics – indicate how closely the software conforms to implicit and explicit customer requirements (i.e., fitness for use)
technical metrics – focus on the properties of the software rather than the process through which the software was developed
size-oriented metrics – direct measures of software development output and quality
function-oriented metrics –indirect measures of software properties
human-oriented metrics – provide information on the manner in which people develop software and human perceptions about the effectiveness of tools and methods

## Slide 12
ESTIMATION — FINAL THOUGHTS
incomplete and imprecise requirements hinder accurate cost estimation
under uncertainty, develop resource requirements incrementally
a cost estimation model is doing well if it can estimate software development costs within 20% of actual costs, 70% of the time on its “own turf”
always perform estimation in more than one way and do cross-checks on your results
essential to have experienced developers do estimating
automated tools can help

## Slide 13
RISK PLANNING
If you do not actively attack risks, they will actively attack you!
  T. Gilb
try to:
  determine what can go wrong, before it happens
  determine its impact
  determine the likelihood that it could happen
  develop cost-effective contingency plans (what to do if it happens)
the ability to do this well is one of the important qualities of a good manager
related to preventive management (i.e., determine the risk and execute preventive action before the problem can take place)

## Slide 14
RISK ANALYSIS
Risk is one of the few certainties of life!
project risks
  budget, schedule, personnel, resource, customer, requirements problems, …
technical risks
  design, implementation, interfacing, testing, maintenance, …
business risks
  no market, no need, sales force can’t sell, no management support, ...
it is important to identify all the risks that we can
use a risk checklist

## Slide 15
RISK PROJECTION (ESTIMATION)
likelihood (li) of the risk (ri)
  establish a scale  Boolean, subjective, probabilities
consequences and impact (xi) of the risk
  its nature  what is likely to happen
  its scope  what is likely to be affected and to what degree
  its timing  when and duration
accuracy of projection
  basis for likelihood and impact
prioritize risks

## Slide 16
RISK MANAGEMENT AND MONITORING
What steps can be taken to mitigate this risk?
“If you know the enemy and you know yourself, you need not fear the result of a hundred battles.”
The Art of War, Sun Tzu
need to perform cost/benefit analysis of countermeasures
Do they cost more than the consequences of the risk itself?
apply 80:20 rule: 80% of all project risk is accounted for by 20% of identified risks

## Slide 17
WORK BREAKDOWN STRUCTURE (WBS)
breaks the project into tasks, sub-tasks, …  divide and conquer
  usually shown in a tree structure
  identify all the activities/tasks required to complete the project
  estimate resources required for each leaf node and then “roll-up” to get estimate for the entire project
  used in both budgets (cost of task) and schedules (time to do task)
WBS should allow each task to be:
  easily planned  has a well-defined start and end
  easily assigned  to individuals/teams
  tracked  can monitor progress and know who is working on it
  budgeted  has an associated cost
  of the right granularity  not too small and not too large

## Slide 18
SCHEDULES
need to determine schedule items and when they happen
  task ordering  dependencies (sequential, parallel)
  time estimates for each task  start time, duration (range?)
  resource assignment  people, hardware, software
  milestones  important management decision points
  deliverables  specifications, documents, code, etc.
  critical path  chain of tasks which determine project duration
prioritize by risk, criticality, resource utilization
usually three levels of schedule needed:
  master schedule  for communicating with management, customer
  macroschedule  for day-to-day management of project
  microschedule  for team management
Gantt and PERT charts commonly used

## Slide 19
STAFFING AND ORGANIZATION
create a (hierarchical) project organization chart that:
  identifies project roles and responsibilities
  plans the number of staff in each role
  establishes product teams as needed
    interdisciplinary teams to coordinate certain efforts
team organization should:
  be modular to limit communication and complexity of interaction
  invest each team member with a clear sense of ownership
this implies that:
  teams should be formed to “own” the design and implementation of one or more packages
  classes should be assigned to individuals for design and implementation
  owners (leads) should be identified for packages and the system
achieving right level of communication is key to success

## Slide 20
TIME-PHASED BUDGET
a time-phased budget details
  when the project’s budget is planned to be spent
  what is expected to have been accomplished at each level of expenditure
manpower will likely be your major cost
  to each WBS item assign costs based on duration, staffing level, and cost for each type of staff
BUT, don’t forget other costs!
  travel – software licenses
  hardware – etc.
  plus some reserve (between 10-15%)
track your spending!
  compare planned and actual money spent against planned and actual completion monthly

## Slide 21
METRICS PLAN
for purposes of project management we need to:
  identify which development metrics to collect
  provide a plan for how to collect each of them
  describe procedures and tools the will be used to collect them
project management metrics are usually related to size:
  number of use cases
  number of classes
  lines of source code
compare planned sizes with current sizes to determine:
  progress: how much of the planned development is in place
  stability: how much change has there been in project requirements and change estimates

## Slide 22
PROJECT TRACKING AND CONTROL
“software projects fall behind schedule one day at a time”
need to have constant, consistent, inoffensive monitoring of project activities
  primary purpose is to make sure the project is meeting the budget and schedule
change is nearly inevitable despite best efforts to minimize it
  key is to handle it in a controlled manner  SCM
“Adding manpower to a late software project makes it later.”
Frederick P. Brooks The Mythical Man-Month

## Slide 23
METHODS OF PROJECT TRACKING & CONTROL
project status meetings  weekly, monthly
doing project reviews and evaluating the results of each review
check if milestones are accomplished as planned
compare actual budget with planned budget and actual start dates with planned start dates for activities
informal chats with project staff
if slipping
  diagnose and recover as best you can: reorganize, change schedule, etc.

## Slide 24
MANAGING SOFTWARE DEVELOPMENT SUMMARY
“Manage the process, don’t let the process manage you.”
Khoa Nguyen, CEO Videoserver